## Slide 1: Paper discussion: Steffi, Sasha, Rhythima
25 Nov 2022

## Slide 2: Timeline
Dates | Work task | Overall Deadlines/ Review
25 Nov | Model: all views have all parameters allocated Model: environments reactivated | Discussion (SSR): Section 2.1 + Figure 1 + Table 1
27 – 28 Nov | Work on the model: string to integer table fix columns | 
28 Nov | Writing: Check figure 2 and add all available buildings Check, maybe remove Table 3 | 
29 Nov | Meeting Rene (discuss final results) Work on the model Writing: Write Section 2.2. Model (Explain Figure 1) Fix Table 2 (move to SI) Move SI to excel | Sasha checks Writings on Section 2.2,
30 Nov | (re) Write Section 2.2.1 Process User Inputs Write Section 2.2.2. Calculate U Values | 
1 Dec | Model locate how to ventilation parameters fix (for writing) Figure 1 + new: Ventilation flow chart concept Finish Section 2.2.3 Space heating demand ------------------------------------------------------------------------------------------- (re) Write Section 2.3. Case study (and Table 3) Write Section 2.3.2. Scenario assessment Section 2.3.1 | 

## Slide 3: Timeline
Dates | Work task | Overall Deadlines
2 Dec | Write Section 2 Methodology intro Improve Section 2.3 | Sasha checks writing Check LCA calculations (KBOB sources) and adapt writing 2.2.3
3 Dec | Results section Figure on U Values (Figure 2) Check Figure 4 : add operational and embodied Model: check new results with ventilation check / edit figure 3, table 4 check model scenario setup: Figure 5 , table 2 | Send the draft to Steffi on Section 2
5 Dec |  | Discussion (SSR): Section 2
6 Dec |  | 
7 Dec |  | 

## Slide 4: Agenda
Paper
Model & Results
Old plan till 24 Nov

## Slide 5: Paper – Methodology structure

## Slide 6: Paper – Data description (table)

## Slide 7: Paper – Data description (writing)

## Slide 8: Paper – Method structure (diagram)

## Slide 12: Model / Results - edits
Heat demand
  Fixed the views on the server database and dependencies
  Ventilation effects and window configurations discussed
LCA
  Introduced embodied and operational