## Slide 1: Paper discussion: Steffi, Sasha, Rhythima
25 Nov 2022

## Slide 2: Timeline - Method
Dates | Work task | Overall Deadlines/ Review
25 Nov | Model: all views have all parameters allocated Model: environments reactivated | Discussion (SSR): Section 2.1 + Figure 1 + Table 1
27 – 28 Nov | Work on the model: string to integer table fix columns | 
28 Nov | Writing: Check figure 2 and add all available buildings Check, maybe remove Table 3 | 
29 Nov | Meeting Rene (discuss final results) Work on the model Writing: Write Section 2.2. Model (Explain Figure 1) Fix Table 2 (move to SI) , Move SI to excel | Sasha checks Writings on Section 2.2,
30 Nov | (re) Write Section 2.2.1 Process User Inputs Write Section 2.2.2. Calculate U Values | 
1 Dec | Model locate how to ventilation parameters fix (for writing) Figure 1 + new: Ventilation flow chart concept Finish Section 2.2.3 Space heating demand -------------------------------------------------------------------------------------- (re) Write Section 2.3. Case study (and Table 3) Write Section 2.3.2. Scenario assessment , Section 2.3.1 | Sasha checks writing Check LCA calculations (KBOB sources) and adapt writing 2.2.3
2 Dec | Write Section 2 Methodology intro Improve Section 2.3 | 
4 Dec | Proofreading | Send the draft to Steffi on Section 2

## Slide 3: Timeline – Results
Dates | Work task | Overall Deadlines
5-6 Dec | Fix timeline Comments on the paper writing | Discussion (SSR): Section 2
7-8 Dec | Leave | 
9 Dec | Writing results structure/ format Model: Convert string and integers PGadmin | 
12-14 Dec | Model: Fix postgres issues Check and fix U Values – figure 2 | Check paper comments section 2-4 Figure 1, table 1, alignment of tables/figs in the doc, final comment check Discuss the results writing format
15 Dec | Section 5.1 U values writing | 
16 Dec | Section 5.2 Heating demand writing Section 5.3 LCA | 
17 Dec | Section 5.4 Scenarios | 

## Slide 4: Timeline – Results
Dates | Work task | Overall Deadlines
4 Jan | Postgres checks | 
5 Jan | Check calculations on heating demands With ventilation effects (direct calculations updates!) | 
6 Jan | Section 5.2 Heating demand writing Check / edit figure 3, table 5 | 
7-8 Jan | LCA reading and updates | 
9 Jan | LCA updates | 
10 Jan | LCA reproducibility | 
11 Jan | LCA mfh02 results Section 5.3 LCA writing outline | Section 5.2 Heating demand writing check Section 5.3 LCA writing check
12 Jan | Planning | Meeting and discussions

## Slide 5: Timeline – Results
Dates | Work task | Overall Deadlines
16 Jan | LCA all results | 
17 Jan | Write Section 4.1. U Values, 4.2. Space heating | LCA remaining results?
18 Jan | Write Section 4.3. LCA | Review sections 4.1-4.3
19 Jan | Scenarios results + Write Section 4.4 Scenarios | Review section 4.4 + Discussion pointers
20 Jan | Discussion points / writing | Discussion review + Send draft Steffi
23 Jan | Conclusion + Abstract | 
24 Jan | Letter to editor + SI check | 
25 Jan | Code check + data push github | Final review send Steffi
26 Jan | Check the journal guidelines completely | 
27 Jan | Submit paper | Submit paper

## Slide 6: U Values
Chart: U Values for roof, floors and walls [W/m2K]
| reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | reported | calculated | roof | floor | wall | roof | floor | wall | roof | floor | wall | roof | floor | wall | roof | floor | wall | roof | floor | wall | roof | floor | wall | MFH02 | MFH03 | MFH07 | MFH08 | MFH10 | MFH11 | MFH12
 | 0.105 | 0.301 | 0.197 | 0.108 | 0.121 | 0.128 | 0.11 | 0.17 | 0.1 | 0.141 | 0.1 | 0.115 | 0.11 | 0.1 | 0.32 | 0.19 | 0.21 | 0.21 | 0.1 | 0.1 | 0.1 | 0.05 | 0.1 | 0.06 | 0.17 | 0.13 | 0.18 | 0.19 | 0.15 | 0.13 | 0.1 | 0.07 | 0.16 | 0.09 | 0.1 | 0.11 | 0.08 | 0.09 | 0.1 | 0.08 | 0.11 | 0.27

## Slide 7: Results
Overall LCA
Embodied emissions
  Components of the building
Operational emissions
  Space heating
  Ventilation

## Slide 8: LCA extensions
Overall LCA
Embodied emissions
  Components of the building
  + Transportation
    as assumed by Viola - lorry transportation of local and not local material till the building site)
Operational emissions
  Space heating
  Ventilation
  + Hot water
    directly associated to the reported values of hot water usage)
  + Electricity
    as assumed by viola based on occupancy)

## Slide 9: 1. Overall LCA - Embodied and operational (Example building)
Chart: LCA GHG GWP100a for MFH02 [kg CO2eq/m2/year]
| Reported (John, 2012) | Calculated
Floor | 0.729 | 0.7711
Ceiling | 2.87 | 3.5315
External wall | 6.02 | 6.2025
Internal wall | 1.37 | 1.0968
Roof | 2.3 | 2.9717
windows | 1.54 | 1.8
electricity | 0.52 | 0.7
transport | 0.708 | 0.91
heating demand | 1.19 | 1.901
ventilation demand | 0.767 | 1.01
hot water | 0.843 | 0.87
Results on paper will show all buildings
Notes: Climate data – how it changed over years
Indoor temperature assumptions by Viola and Rene (reasons for differences)
Heat exchangers (assumptions to mention from Rene)

## Slide 10: 2. Embodied : components (Example building)
Chart: MFH02 LCA [kg CO2eq/m2/year]
| Floor | Ceiling | External wall | Internal wall | Roof
Reported (John, 2012) | 0.729 | 2.87 | 6.02 | 1.37 | 2.3
Calculated | 0.7711 | 3.5315 | 6.2025 | 1.0968 | 2.9717

## Slide 11: 2. Embodied emissions: methodology
Material inventory database
KBOB <-> Ecoinvent mapping

## Slide 12
Material inventory database
KBOB <-> Viola’s material mapping
2. Embodied emissions: methodology

## Slide 13: 2. Embodied emissions: methodology
Pipeline for each building + each component + each material

## Slide 14: 3. Operational emissions : space heating + ventilation + hot water
Chart: Space heating demands [MJ/ m2/year ]
| mfh01 | mfh02 | mfh03 | mfh04 | mfh05 | mfh07 | mfh08 | mfh10 | mfh11 | mfh12
Reported (Viola) | 10.8 | 8.8333 | 5.8333 | 14.1083 | 9.8333 | 4 | 6.5 | 9.5833 | 1.9167 | 2.3417
Calculated | 8.6775 | 13.9975 | 6.3042 | 14.6867 | 5.935 | 3.6067 | 5.89 | 9.1567 | 2.6692 | 5.7042
Calculated (only material updated)
Default (Buffat) | 6.7158 | 19.2308 | 8.73 | 14.78 | 5.7125 | 3.5508 | 9.9492 | 13.26 | 14.2392 | 8.9858

## Slide 15: 3. Operational : all components (example building)
Chart: MFH02 LCA [kg CO2eq/m2/year]
| heating demand | ventilation demand | hot water
Reported (John, 2012) | 1.19 | 0.767 | 0.843
Calculated | 1.901 | 1.01 | 0.87

## Slide 16: Comments Section 2-4
Figure 1 + Table 1
  Dimensions of building components
Ventilation data and updates

## Slide 17: U values results
Internal walls removed
U Values rechecked
  Some large values for buildings estimated with high space heating demands
  Rechecked for the given values vs calculated – which one to use?
U Values windows updates

## Slide 18: U Values writings
All results presented
Significant p values shown for given
Same p values against buffat

## Slide 19: Heat demand results

## Slide 20: Heat demand writings

## Slide 21: LCA results

## Slide 22: LCA writings

## Slide 23: Title of the paper
Keywords
LCA of buildings
User tool
Material data integration
--------------------
New
Integration of materials in operational and embodied building impacts: tool for future renovation scenarios
Integration of materials in life cycle assessment (LCA) of buildings: tool for future renovation scenarios
------------------------
Old: Combined material-energy building environmental footprint model: assessment of future renovation scenarios

## Slide 24: Paper – Methodology structure

## Slide 25: Paper – Method structure (diagram)

## Slide 26: Paper – Model (writing)

## Slide 27: Paper – Case study (writing)

## Slide 28: Agenda
Paper
Model & Results
Old plan till 24 Nov

## Slide 29: Paper – Data description (table)

## Slide 30: Paper – Methodology structure

## Slide 31: Paper – Data description (writing)

## Slide 32: Paper – Method structure (diagram)

## Slide 36: Model / Results - edits
Heat demand
  Fixed the views on the server database and dependencies
  Ventilation effects and window configurations discussed
LCA
  Introduced embodied and operational